## Project schedule
| Capstone Project |  |  |  |  | Project start: | [7 empty] | 2026-03-08
| Project - 3 | Numika Shetty |  | Raja Kumar |  | Display week: | [7 empty] | 1
| ABADS 20 | Chandan Chauhan |  | Vilakshan Kumar
[6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23
| TASK | PROGRESS | START | END |  | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29
[6 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Kick-Off & Scope Lock
| Confirm objective | 100% | 2026-03-08 | 2026-03-09 | 2
| Enforce leakage rule | 100% | 2026-03-09 | 2026-03-09 | 1
| Decide dataset approach (use mat only OR train on one and sanity-check on the other) | 100% | 2026-03-09 | 2026-03-09 | 1
| Fix Metrics (MAE/RMSE/R²) | 100% | 2026-03-09 | 2026-03-09 | 1
| Define Repo + Naming Conventions | 100% | 2026-03-10 | 2026-03-09 | 0
Data Loading & Validation
| Load CSV(s) & Validate Schema | 100% | 2026-03-08 | 2026-03-09 | 2
| Confirm no missing values | 100% | 2026-03-08 | 2026-03-09 | 2
| Identify categorical vs ordinal vs numeric | 100% | 2026-03-08 | 2026-03-09 | 2
| Verify target range (0–20) | 100% | 2026-03-08 | 2026-03-09 | 2
| Remove G1/G2 from feature set | 100% | 2026-03-08 | 2026-03-09
| Version Clean Dataset | 100% | 2026-03-08 | 2026-03-09
Decision-Oriented EDA
| G3 distribution | 100% | 2026-03-09 | 2026-03-10 | 2
| Key Relationships | 100% | 2026-03-09 | 2026-03-10 | 2
| Subgroup Patterns | 100% | 2026-03-09 | 2026-03-10 | 2
| Confirm leakage impact by showing correlation of G1/G2 with G3 (EDA only) | 100% | 2026-03-09 | 2026-03-10 | 2
| Define Intervention Hypotheses | 100% | 2026-03-09 | 2026-03-10
Preprocessing & Encoding Pipeline
| Build Preprocessing Pipeline | 100% | 2026-03-10 | 2026-03-11 | 2
| Treat Ordinal Scales Properly | 100% | 2026-03-10 | 2026-03-11 | 2
| Ensure consistent columns across splits | 100% | 2026-03-10 | 2026-03-11 | 2
| Save Feature List | 100% | 2026-03-10 | 2026-03-11 | 2
Split Strategy & Reproducibility
| Create train/val/test | 100%
| Stratify by grade bins to preserve distribution | 100%
| Fix Random Seed & Save Indices | 100%
Feature Engineering
| Create derived features | 100%
| Update feature dictionary | 100%
Train Baseline XGBRegressor
| Train baseline XGBRegressor | 100%
| Establish baseline RMSE/MAE on validation | 100%
Hyperparameter Tuning + Early Stopping
| RandomizedSearchCV or manual tuning + early stopping using validation RMSE | 100%
| Tune Depth, Learning Rate, Subsample, Colsample, Regularization Parameters | 100%
| Log Experiments | 100%
Final Model Training
| Retrain with best params (train + val) | 100%
| Save model artifact and preprocessing artifact | 100%
Final Evaluation (Test Set)
| Evaluate MAE/RMSE/R² | 100%
| Plot Predicted vs Actual | 100%
| Residual Distribution & Error by grade bands | 100%
Error Slicing & Interpretation
| Slice errors by parameters | 100%
| Model Under/Over-prediction Identification & Intervention Translation | 100%
Clustering Dataset Build
| Build clustering matrix & Scale features | 100%
| Decide feature subset for interpretability & PCA for visualization | 100%
Clustering & Cluster Cards
| K-means + hierarchical cross-check | 100%
| Build “cluster cards” & Recommend Support Strategy | 100%
Final Report, Slides & Demo
| Finalize Report | 100% | 2026-03-26 | 2026-03-27 | 2
| Finalize Report Summary | 100% | 2026-03-26 | 2026-03-27 | 2
| Finalize PPT (slides) | 100% | 2026-03-27 | 2026-03-29 | 3
README file with "How To Run"
| Gantt Chart | 100% | 2026-03-08 | 2026-03-29 | 22
Formulas:
Display week: = [Display week:, row below]